## Project Details
id | name | client | lead | employee | status | start | end | po | desc | manual_hrs | auto_hrs | cost_per_hr | hours_saved | cost_saved | roi_pct | is_new
1 | Raychem GATE Entry and GRN Process - Part A | Raychem | Vikram | Nandukanth, Radhika | R&M | 20/07/2025 |  | 456788 | GATE Entry and GRN Creation
2 | PO Creation Process | Swagelok-California | Vikram | Akhila Kovuri | Important | 22/09/2025 | 17/12/2025 | 789747 | Downloading PO Creation Report
3 | Payment Application Process for all Company | Swagelok-California |  | Chethan B N | R&M | 22/09/2025 | 19/01/2026 | 984534 | Posting Cr amount to required Company code
4 | Payments Application Process for LAMPAY | Swagelok-California |  | Chethan B N | Discontinued | 22/09/2025 | 24/02/2026 | 786540
5 | LAMCON Invoice Consignment | Swagelok-California |  | Akhila Kovuri | UAT | 16/10/2025 |  | 983240 | Creating Invoice Number by posting Material Number in SAP B1
6 | CyberSource Application Process | Swagelok-California |  | Akhila Kovuri | PDD | 02/12/2026 |  | 451238
7 | HR Master Data | TEPL | Vikram | Mathan | R&M | 18/06/2022 |  | 933248
8 | MIS Report Process | TEPL |  | Narendra | R&M | 20/04/2024 |  | 84973
9 | PO Parking | TEPL |  | Nandukanth | Completed | 20/11/2024 | 18/01/2025 | 213480
10 | Greeting Process | TEPL |  | Sushma | R&M | 01/03/2025 | 25/03/2025 | 345576
11 | Data Migration from SAP to Salesforce | Swagelok - Alabama | Sushma | Sushma | R&M | 04/03/2025 | 14/05/2025 | 543778 | Moving data from SAP to Salesforce
12 | Tubing SCS Inspection Instructions | Swagelok - Alabama | Sushma | Sushma | Discontinued | 04/04/2025 |  | 432670 | Extraction of Specific data from PDFs
13 | Generate Batch Invoices | Swagelok - Alabama |  | Sushma | R&M | 06/05/2025 | 28/02/2026 | 355377 | Identifying the correct batches in SAP B1
14 | Sorting CTM Requests in ZenDesk | Swagelok - Alabama |  | Chethan B N | Discontinued | 06/10/2025 |  | 872351 | Organizing and prioritizing CTM tickets in Zendesk
15 | Emailed PDF Cert Instructions | Swagelok - Alabama |  | Vikas, Sushma | R&M | 09/03/2025 | 17/11/2025 | 762345 | Extracting the PO numbers from the PDFs
16 | Generate Quotes from Solidworks BOM | Swagelok - Alabama |  | Vikas | UAT | 30/09/2025 |  | 672552 | Creating quotations using data from SolidWorks BOM
17 | Renaming and Saving Quality Records | Swagelok - Alabama |  | Sushma | R&M | 01/08/2026 | 06/02/2026 | 765428 | Renaming and storing quality documents
18 | TDS Process | TEPL |  | Avinash | UAT | 07/10/2025 |  | 267357 | Create TDS report and share to User
19 | GST Process | TEPL |  | Sharan | UAT | 07/10/2025 |  | 872610 | Create GST report and share to User
20 | Job Scheduling - Cancellation Process | TEPL |  | Shiv Shankar | Completed | 22/08/2025 | 01/06/2026 | 465738 | Check for cancellation jobs in SAP and send alert mail
21 | Job Scheduling - Active Process | TEPL |  | Shiv Shankar | Completed | 24/10/2025 | 01/06/2026 | 749474 | Check for Active jobs in SAP and send alert mail
22 | Fixture Automation | TEPL |  | Nischal | UAT | 14/11/2025 |  | 248490 | Download the fixture dump data and append every 2 mins
23 | Invoice Posting | TEPL |  | Mathan | Completed |  |  | 353628 | Need to post the invoices
24 | Vendor Confirmation | TEPL |  | Mathan | Completed | 06/08/2025 | 06/11/2025 | 235367 | Need to confirm the vendor codes
25 | Block Stock Auto Mail Trigger Process | TEPL |  | Chethan B N | R&M | 01/07/2025 | 21/01/2026 | 484640 | Downloading Block Stock Report and send to user
26 | Tool Crib Auto Reservation - FIFO Process | TEPL |  | Shiv Shankar | In Progress | 12/02/2025 |  | 674537 | Reserve the tool crib data in FIFO Order
27 | Tool Crib Posting Goods Issue (GI) - MT 201 | TEPL |  | Nischal | In Progress | 12/02/2025 |  | 380273 | Post Goods Issue to movement type 201
28 | QA32 Dump Process | TEPL |  | Avinash | In Progress | 02/10/2026 |  | 345468 | Download the QA32 Dump file and append every 2 mins
29 | AP Scheduling | TEPL |  | Mathan & Fiaz | PDD | 13/02/2026 |  | 189375 | Create Finance Report
30 | Attendance DB Update - TEPL Assembly & Raw Clock | TEPL |  | Sivin | Completed | 26/12/2026 | 05/02/2026 | 345465 | Downloading and Updating Employee Assembly and Raw Clock data
32 | BOM | TEPL |  | Sharan | Completed
33 | Production Order | TEPL |  | Sharan | Completed
34 | Google Cloud Platform | Internal POC |  | Faiyaz | Internal POC | 15/12/2025 | 10/01/2026 |  | Agentic Platform using Google Cloud and NotebookLM
35 | Microsoft Agent Frontier | Internal POC |  | Faiyaz | Internal POC | 05/11/2025 | 14/11/2025 |  | Agentic Platform using Microsoft Copilot Frontier
36 | UiPath Test Automation | Internal POC |  | Faiyaz | Internal POC | 07/01/2026 |  |  | Explored TestManager, Test Cloud and Test Automation
37 | Qpdf | Internal POC |  | Chandru S | Internal POC | 10/03/2025 | 14/05/2025 |  | Chat with PDF AI
38 | EDI | Internal POC |  | Chandru S & Sivin | Internal POC | 22/05/2025 | 20/06/2025 |  | Conversion of Medicare Insurance PDF to EDI
39 | krista.ai | Internal POC |  | Chandru S | Internal POC | 02/06/2025 |  |  | Agentic Platform using Krista.ai
40 | UiPath with GitHub | Internal POC |  | Chandru S | Internal POC | 20/06/2025 | 24/06/2025 |  | Integrated UiPath usecases with GitHub
41 | Microsoft Copilot Agent with Studio | Internal POC |  | Chandru S | Internal POC | 10/11/2025 |  |  | Agentic Platform using Microsoft Copilot Studio
42 | N8N | Internal POC |  | Chandru S | Internal POC | 07/07/2025 | 09/07/2025 |  | Agentic Platform using N8N
43 | UiPath Standalone | Internal POC |  | Chandru S | Internal POC | 04/02/2026 |  |  | Explored UiPath On-premise Studio, Orchestrator, Test Suite
44 | SHAREPOINT | Internal POC |  | Rubika AE | Internal POC | 24/01/2026 | 23/01/2026 |  | Web Development Project Tracker
45 | AWS - Knowledge Based Agent | Internal POC |  | Rubika AE | Internal POC | 02/02/2026 | 05/02/2026 |  | Agentic Platform using Amazon Bedrock and S3 bucket
46 | Himatsingha | External POC |  | Narendra | External POC | 17/02/2026 | 14/03/2026 |  | Reconciliation of Files to create a template
47 | IBM RPA Tool | Internal POC |  | Sharan | Internal POC
48 | Phantom Pick list | Swagelok-California |  | Akhila | In Progress | 2026-03-16 00:00:00 |  |  | Posting Pick list data
49 | AI Agents | Internal POC | Nanditha | Sivin, Rubika, Faiyaz, Arvind, Chandru S | In Progress | 05/04/2026 |  |  | AI Boot Camp
50 | Raychem Extension | Raychem |  | Nanditha | Completed | 05/04/2026
51 | Internal Reconciliation | Swagelok - Alabama |  | Vikas | In Progress | 12/03/2026 |  |  | Submitting matching records in SAP B1 after doing reconciliation
52 | Claude Project | Internal POC | Vishnu | Vikram, Chandru S | In Progress | 01/04/2026 |  |  | Working on Claude
53 | Infosys Contract | Infosys | Vishnu | Nanditha, Soumya | Completed | 01/10/2025 | 31/03/2026 |  | Full time Contract employee for Infosys
54 | Raychem | Raychem |  | Vishnu | Presales | 28/04/2026 | [8 empty] | TRUE

## Presales_POC
id | name | client | lead | employee | status | start | end | po | desc | manual_hrs | auto_hrs | cost_per_hr | hours_saved | cost_saved | roi_pct | is_new
34 | Google Cloud Platform | Internal POC |  | Faiyaz | Internal POC | 15/12/2025 | 10/01/2026 |  | Agentic Platform using Google Cloud and NotebookLM
35 | Microsoft Agent Frontier | Internal POC |  | Faiyaz | Internal POC | 05/11/2025 | 14/11/2025 |  | Agentic Platform using Microsoft Copilot Frontier
36 | UiPath Test Automation | Internal POC |  | Faiyaz | Internal POC | 07/01/2026 |  |  | Explored TestManager, Test Cloud and Test Automation
37 | Qpdf | Internal POC |  | Chandru S | Internal POC | 10/03/2025 | 14/05/2025 |  | Chat with PDF AI
38 | EDI | Internal POC |  | Chandru S & Sivin | Internal POC | 22/05/2025 | 20/06/2025 |  | Conversion of Medicare Insurance PDF to EDI
39 | krista.ai | Internal POC |  | Chandru S | Internal POC | 02/06/2025 |  |  | Agentic Platform using Krista.ai
40 | UiPath with GitHub | Internal POC |  | Chandru S | Internal POC | 20/06/2025 | 24/06/2025 |  | Integrated UiPath usecases with GitHub
41 | Microsoft Copilot Agent with Studio | Internal POC |  | Chandru S | Internal POC | 10/11/2025 |  |  | Agentic Platform using Microsoft Copilot Studio
42 | N8N | Internal POC |  | Chandru S | Internal POC | 07/07/2025 | 09/07/2025 |  | Agentic Platform using N8N
43 | UiPath Standalone | Internal POC |  | Chandru S | Internal POC | 04/02/2026 |  |  | Explored UiPath On-premise Studio, Orchestrator, Test Suite
44 | SHAREPOINT | Internal POC |  | Rubika AE | Internal POC | 24/01/2026 | 23/01/2026 |  | Web Development Project Tracker
45 | AWS - Knowledge Based Agent | Internal POC |  | Rubika AE | Internal POC | 02/02/2026 | 05/02/2026 |  | Agentic Platform using Amazon Bedrock and S3 bucket
46 | Himatsingha | External POC |  | Narendra | External POC | 17/02/2026 | 14/03/2026 |  | Reconciliation of Files to create a template
47 | IBM RPA Tool | Internal POC |  | Sharan | Internal POC
54 | Raychem | Raychem |  | Vishnu | Presales | 28/04/2026 | [9 empty] | True

## License
id | tool_name | no_of_licenses | start_date | end_date | created_at
2 | Claude | 5 | 2026-04-28 | 2026-05-28 | 2026-04-28T12:45:01
1 | Uipath | 9 | 2026-01-01 | 2026-12-31 | 2026-04-28T12:29:06

## Users
id | name | email | role | is_active | created_at
1 | Admin | admin@qualesce.com | admin | TRUE | 2026-04-28T11:24:10
2 | Chandru | chandru.s@qualesce.com | employee | TRUE | 2026-04-28T11:25:55
3 | Vikram | vikram.r@qualesce.com | lead | TRUE | 2026-04-28T11:29:19
4 | Vishnu | vishnu.v@qualesce.com | manager | TRUE | 2026-04-28T11:32:10
5 | Faiyaz | md.faiyaz@qualesce.com | sales | TRUE | 2026-04-28T15:14:21
6 | Sivin | sivin.ms@qualesce.com | employee | TRUE | 2026-04-28T16:10:40